## Intro
WIP Reporting Sample Template
Brought to you by PivotXL
https://pivotxl.com/
🎯 What This Template Teaches This template is designed to teach you the basics of preparing a Work-in-Progress (WIP) report in Excel. You’ll learn how to: Track contract amounts, costs to date, and cost to complete. Calculate percent complete, earned revenue, and under/over billings. Forecast total job profitability and spot potential margin risks early.
💡 Next Step: Automate It with PivotXL This template is a starting point. PivotXL helps you streamline the cost-to-complete process with project managers and automatically calculate all these metrics — keeping your WIP reports accurate, up-to-date, and ready for decision-making in seconds.
📬 Sign up for Free
https://pivotxl.com/

## Sample WIP Report
Project Name | Total Contract Amount | Cost to Date | Cost to Complete | Total Estimated Cost | Percent Complete (%) | Earned Revenue | Billed Revenue | Under/Over Billed | Gross Profit to Date | Projected Gross Profit
Project A | 100000 | 45000 | 50000 | 95000 | 47.37% | 47368.4211 | 40000 | -7368.4211 | 2368.4211 | 5000
Project B | 250000 | 125000 | 110000 | 235000 | 53.19% | 132978.7234 | 130000 | -2978.7234 | 15000 | 15000
Project C | 150000 | 90000 | 60000 | 150000 | 60% | 90000 | 95000 | 5000 | 0 | 0
For More Information on this template - check out accompanying article
https://pivotxl.com/understanding-wip-reports/